## Sheet1
Date | Description | Total pts | Breakdown | Max pts | Actual | Notes:
2011-09-22 | Management Update | 20 | Initial phase 2 meeting notes: when where who | 1
|  |  | Alpha use cases | 5 |  | 5 points: alpha use cases are (a) identified and prioritized, (b) represent core gameplay, (c) seem feasible | 3 points: Use cases are identified and prioritized but (b) -(c) are inadequately met or the uses cases are not sufficiently elaborated to so that (b) - (c) can be evaluated. | 0: No use cases identified or so poorly described that we cannot understand/assess them.
|  |  | Goals | 6 |  | 6 points: (a) All phase 2 goals are identified, (b) current risks and all longterm major risks are identified and back-up plans discussed , (c) goals are prioritized in a way that reflects risks , (d) high priority goals are well described with concrete outcomes and good time estimates (less than 3 hours each). We are left feeling informed, confident the project is on track. | 3 points: Most of (a)-(d) are covered but some important details/rationale are missing. We are left asking important questions. | 0 pt: Serious lack of detail/rationale. We have no idea what is going on.
|  |  | Plan | 6 |  | 6 pts: (a) Plan is appropriate given longterm schedule, (b) Plan is feasible, (c) Team member assignments and intermediate deadlines are reasonable, (d) tickets are issued for all work assignjments.We are left feeling informed, confident the project is on track. | 3 points: Most of (a)-(c) are covered but we are left asking important questions. | 0 pts: Serious lack of detail/rationale. We have no idea what is going on.
|  |  | Blog entry | 2 |  | 2 point: Blog update is clear, concise, and appropriate for audience
2011-09-27 | Management Update | 20 | Meeting notes: when where who | 1
|  |  | Meeting: Progress report | 5 |  | 5 pts: (a) What was done, (b) What wasn't done, (c) all members completed work log, (d) actual time to complete vs. estimates discussed, (e) Process improvements identified as needed as well as plans to implement the improvements | 3 pts: Too many details are missing to adequately assess progress or the week didn't go as planned and the team has not clearly identified why and how to prevent it from happening again | 0 pts: missing
|  |  | Meeting: Goals | 6 |  | see first management report | see first management report | see first management report
|  |  | Meeting: Plan | 6 |  | " | " | "
|  |  | Blog entry | 2 |  | " | " | "
2011-09-27 | Architectural Design 1st draft | 30 | Use cases | 6 |  | 6 pts: Most of the rubric scores marked highly agree | 3 pts: Most rubric items marked neutral | 0 pts: Most rubric items marked strongly disagree
|  |  | Domain Diagram | 6 |  | " | " | "
|  |  | Class Diagrams | 6 |  | " | " | "
|  |  | Sequence Diagrams | 6 |  | " | " | "
|  |  | Analysis | 6 |  | " | " | "
2011-09-27 | Prototype/Code 1 | 30 | Plan | 5 |  | 5 pts: A reasonable and measurable goal is clearly articulated. | 3 pts: Plans and how they will be evaluated are somewhat vague or goal is unreasonable (infeasible or too simple) | 0 pts: no plans or success metric provided
|  |  | Rationale | 5 |  | 5 pts: A convincing rationale is provided for the goal | 3 pts: Rationale is not entirely convincing | 0 pts: no rationale provided
|  |  | Prototype execution | 15 |  | 15 points: Excellent, does exactly what it is supposed to | 10 pts: runs with some bugs and does not quite measure up to goal | 5 pts: serious problems and misses the mark | 0 pts: not completed
|  |  | Assessment | 5 |  | 5 pts: Results are assessed and lessons learned are discussed. | 3 pts: Assessment misses important questions. | 0 pts: No assessment is made
2011-10-04 | Management Update | 20 | Meeting notes: when where who | 1
|  |  | Meeting: Progress report | 5 |  | see previous management report | see previous management report
|  |  | Meeting: Goals | 6 |  | " | "
|  |  | Meeting: Plan | 6 |  | " | "
|  |  | Blog entry | 2 |  | " | "
2011-10-04 | Architectural Design 2nd draft | 30 | Use cases | 6 |  | 6 pts: Most of the rubric items marked highly agree | 3 pts: Most rubric items marked neutral | 0 pts: Most rubric items marked strongly disagree
|  |  | Domain Diagram | 6 |  | " | " | "
|  |  | Class Diagrams | 6 |  | " | " | "
|  |  | Sequence Diagrams | 6 |  | " | " | "
|  |  | Analysis | 6 |  | " | " | "
2011-10-04 | User Interface Design | 40 | Design | 20 |  | 20 pts: most rubric items marked strongly agree | 10 pts: most rubric items marked neutral | 0 pts: Most rubric items marked strongly disagree
|  |  | Rationale | 5 |  | 5 pts: most rubric items marked strongly agree | 3 pts: most rubric items marked neutral | 0 pts: Most rubric items marked strongly disagree
|  |  | Analysis | 5 |  | " | " | "
2011-10-04 | Prototype/Code 2 | 30 | Plan | 5 |  | 5 pts: A reasonable and measurable goal is clearly articulated. | 3 pts: Plans and how they will be evaluated are somewhat vague or goal is unreasonable (infeasible or too simple) | 0 pts: no plans or success metric provided
|  |  | Rationale | 5 |  | 5 pts: A convincing rationale is provided for the goal | 3 pts: Rationale is not entirely convincing | 0 pts: no rationale provided
|  |  | Prototype execution | 15 |  | 15 points: Excellent, does exactly what it is supposed to | 10 pts: runs with some bugs and does not quite measure up to goal | 5 pts: serious problems and misses the mark | 0 pts: not completed
|  |  | Assessment | 5 |  | 5 pts: Results are assessed and lessons learned are discussed. | 3 pts: Assessment misses important questions. | 0 pts: No assessment is made