## Slide 1: Let the fun begin!

## Slide 2: Your Goal stack for iteration 8!
Beta
Done!

## Slide 3: Your major milestones for main Game Project!
Beta walk through (12/13)
Alpha walk through (11/8)
UI/Concept prototype test (10/9)
Design review (10/16)
Test plan review (10/25)
Customer elicitation (10/2)
Usability test (10/30)

## Slide 4: Customer elicitation
Starts at about 3:30 today
Prep:
Review learning objectives
Select discipline (at most 2 teams per discipline)
Come up with questions you want to ask
  You need to understand your users (middle school students)
  You need to understand your customers (teachers)
  You need to understand the context (classroom)
Lecture will resume after the elicitation.

## Slide 5: Project
Project iterations run from the start of class on Tuesday
Tuesday group meetings:
  Assess results of previous week
  Analyze risks
  Update goal stack
  Formulate plan for week
  Communicate with customers
  Post meeting notes

## Slide 6
For example, …

## Slide 7: Analyze risks
What are the biggest risks confronting the project? (Note these risks may have to do with goals down in the goal stack.)
How/when can you mitigate this risk?
What is your back up plan?

## Slide 8
Beta walk through (12/13)
Alpha walk through (11/8)
UI/Concept prototype test (10/9)
Alpha design review (10/16)
Test plan review (10/25)
Usability test (10/30)
Paper prototype of basic game concept
Review of your design for the alpha
Test of your UI design
Review of your testing procedures
Risk: What is our concept?

## Slide 9: What is our concept?
Choose your learning objective
Research/analyze other games that target the objective/audience
Define & prioritize your design goals
Brainstorm to come up with several concepts
Critique your concepts
Ask questions
Choose one
Choose backup
You may need to iterate.

## Slide 10
Beta walk through (12/13)
Alpha walk through (11/8)
UI/Concept prototype test (10/9)
Alpha design review (10/16)
Test plan review (10/25)
Usability test (10/30)
Paper prototype of basic game concept
Review of your design for the alpha
Test of your UI design
Review of your testing procedures
Risk: What is our concept?
Risk: Is it a good concept?

## Slide 11: UI/Concept test
Can we achieve our design goals with our choice of concept? How can a UI/Concept test help us answer this question?
Decide the questions we want to answer with the UI/Concept test
Write use cases for prototype
Implement the prototype
Practice running the test

## Slide 12
Beta walk through (12/13)
Alpha walk through (11/8)
UI/Concept prototype test (10/9)
Alpha design review (10/16)
Test plan review (10/25)
Usability test (10/30)
Paper prototype of basic game concept
Review of your design for the alpha
Test of your UI design
Review of your testing procedures
Risk: What is our concept?
Risk: Is it a good concept?
Risk: Can we build it?

## Slide 13: Feasibility
What are the major requirements?
  Menus
  Sprites
  Gestures
  Physics
  AI
  Art
  …
Do we know how to do these things? Can we find an engine/tools to help? Are they worth the trouble?

## Slide 14
UI/Concept test (10/9)
Check out other games
Ask questions
Define & prioritize design goals
Choose learning objective
Choose concept (and backup)
Brainstorm concepts
Critique concepts
Analyze concept vs. design goal
risks
Decide questions to answer with
UI/Concept test
Implement prototype
Practice test
Write use cases
Research/assess tools/engines
Identify major functional
requirements

## Slide 15: Update goal stack
Eliminate any goals/task that have been achieved/completed
Add new goals based on
  your risk analysis
  assessment of previous week’s work
  clarification of goals
  new milestones assigned/suggested for week by Z
Reprioritize

## Slide 16
Depending on what you get done today our goal stack could look like this.
Beta walk through (12/13)
Alpha walk through (11/8)
Alpha design review (10/16)
Test plan review (10/25)
Usability test (10/30)
Choose concept (and backup)
Implement UI/Concept prototype
Practice UI/Concept test
Write use cases
Research/assess tools/engines
Identify major functional
requirements
Decide questions to answer with
UI/Concept test

## Slide 17: Formulate plan
What goals are “must do” for the coming week?
What goals are “should do” for the coming week?

## Slide 18
MUST DO
Beta walk through (12/13)
Alpha walk through (11/8)
Alpha design review (10/16)
Test plan review (10/25)
Usability test (10/30)
Choose concept (and backup)
Implement UI/Concept prototype
Practice UI/Concept test
Write use cases
Research/assess tools/engines
Identify major functional
requirements
Decide questions to answer with
UI/Concept test

## Slide 19: Formulate plan
For each “must do” and “should do” goal, clarify the tasks that need to be completed in order to achieve the goal.
Each task should have a concrete, demonstrable outcome.
The outcomes for the tasks associated with a goal should, collectively, demonstrate that the goal is achieved.

## Slide 20
This is concrete and measurable. But all decisions have an implicit “rationale” that needs to be documented, usually in team meeting notes.
Beta walk through (12/13)
Alpha walk through (11/8)
Alpha design review (10/16)
Test plan review (10/25)
Usability test (10/30)
Choose concept (and backup)
Implement UI/Concept prototype
Practice UI/Concept test
Write use cases
Research/assess tools/engines
Identify major requirements
Decide questions to answer with
UI/Concept test

## Slide 21
This also involves decisions that need documenting.
Analyze concept vs. design goal
risks
Decide how to use UI/Concept test
to mitigate risks
Beta walk through (12/13)
Alpha walk through (11/8)
Alpha design review (10/16)
Test plan review (10/25)
Usability test (10/30)
Choose concept (and backup)
Implement UI/Concept prototype
Practice UI/Concept test
Write use cases
Research/assess tools/engines
Identify major requirements
Decide questions to answer with
UI/Concept test

## Slide 22
Way too vague.
Beta walk through (12/13)
Alpha walk through (11/8)
Alpha design review (10/16)
Test plan review (10/25)
Usability test (10/30)
Choose concept (and backup)
Implement UI/Concept prototype
Practice UI/Concept test
Write use cases
Research/assess tools/engines
Identify major requirements
Decide questions to answer with
UI/Concept test
Identify game engines
Identify functionality provided
Build small prototype to assess
Suitability & learning curve
Identify art tools
Identify functionality provided
Develop concept art to assess
suitability & learning curve

## Slide 23: Formulate plan
Estimate how long each task will take. If a task will take more than 3 hours it is too big, break it down into smaller tasks.

## Slide 24
Identify game engines
Identify functionality provided
Build small prototype to assess
Suitability & learning curve
Beta walk through (12/13)
Alpha walk through (11/8)
Alpha design review (10/16)
Test plan review (10/25)
Usability test (10/30)
Choose concept (and backup)
Implement UI/Concept prototype
Practice UI/Concept test
Write use cases
Research/assess tools/engines
Identify major requirements
Decide questions to answer with
UI/Concept test
Identify art tools
Identify functionality provided
Develop concept art to assess
suitability & learning curve
1 hour discussion at meeting

## Slide 25
Identify game engines
Identify functionality provided
Build small prototype to assess
Suitability & learning curve
3 hours
Beta walk through (12/13)
Alpha walk through (11/8)
Alpha design review (10/16)
Test plan review (10/25)
Usability test (10/30)
Choose concept (and backup)
1 hour
Implement UI/Concept prototype
- 3 hours
Practice UI/Concept test – 1 hour
Write use cases – 2 hours
Research/assess tools/engines
Identify major functional
Requirements – 1 hour
Decide questions to answer with
UI/Concept test – 30 minutes
Identify art tools
Identify functionality provided
Develop concept art to assess
suitability & learning curve
3 hours

## Slide 26: Formulate plan
Sketch Pert/Gantt charts
Assign intermediate deadlines
Assign tasks/schedule meetings
Create tickets

## Slide 27
Identify game engines
Identify functionality provided
Build small prototype to assess
suitability & learning curve
3 hours
Choose concept (and backup)
1 hour
Implement UI/Concept prototype
- 3 hours
Practice UI/Concept test – 1 hour
Write use cases – 2 hours
Identify major requirements –
1 hour
Decide questions to answer with
UI/Concept test – 30 minutes
Identify art tools
Identify functionality provided
Develop concept art to assess
suitability & learning curve
3 hours
Pert Chart

## Slide 28
Identify game engines
Identify functionality provided
Build small prototype to assess
suitability & learning curve
3 hours
Choose concept (and backup)
1 hour
Implement UI/Concept prototype
- 3 hours
Practice UI/Concept test – 1 hour
Write use cases – 2 hours
Identify major requirements –
1 hour
Decide questions to answer with
UI/Concept test – 30 minutes
Identify art tools
Identify functionality provided
Develop concept art to assess
suitability & learning curve
3 hours
Pert Chart
Meet Wed. 9 PM and do
In group

## Slide 29
Identify game engines
Identify functionality provided
Build small prototype to assess
suitability & learning curve
3 hours
Choose concept (and backup)
1 hour
Implement UI/Concept prototype
- 3 hours
Practice UI/Concept test – 1 hour
Write use cases – 2 hours
Identify major requirements –
1 hour
Decide questions to answer with
UI/Concept test – 30 minutes
Identify art tools
Identify functionality provided
Develop concept art to assess
suitability & learning curve
3 hours
Pert Chart
Group meet Wed. 9 PM and do
In group
Alice & Bob, due by Saturday
10 AM
Group meet Saturday 10AM to review

## Slide 30
Identify game engines
Identify functionality provided
Build small prototype to assess
suitability & learning curve
3 hours
Choose concept (and backup)
1 hour
Implement UI/Concept prototype
- 3 hours
Practice UI/Concept test – 1 hour
Write use cases – 2 hours
Identify major requirements –
1 hour
Decide questions to answer with
UI/Concept test – 30 minutes
Identify art tools
Identify functionality provided
Develop concept art to assess
suitability & learning curve
3 hours
Pert Chart
Group meet Wed. 9 PM and do
In group
Alice & Bob, due by Saturday
10 AM
Group meet Saturday 10AM to review
Alice & Bob, due by Tuesday start of class.
Carol & David, due by Tuesday start of class

## Slide 31: Communicate with customer
Review weekly plans/progress with me
Send questions for the teachers to me
Bi-weekly blog post aimed at students
  Progress report
  Questions

## Slide 32: Post meeting notes
Every meeting should have a scribe (you can rotate this)
The scribe should document your discussions and your decisions
The scribe should post meeting notes to the trac

## Slide 33: trac
Create new goal stack for week
Document discussions/decisions (meeting notes)
Issue tickets
Maintain personal work logs

## Slide 34: Sudoku project assessment
http://www.surveymonkey.com/s/SKYDF5G