## Sheet1
General category | Category | Attribute | Rating
|  |  | Strongly agree | Somewhat agree | Neutral | Somewhat disagree | Strongly disagree
Meeting notes (at least one per week) | Logistics | Notes include when and where the meeting took place, who was there, who wasn't and why, and who scribe.
| Summary | Notes include clear and comprehensive summary of discussion and decisions
Weekly assessment and planning report | Assessment of past week | Goals: status update provided on goals/tasks due this week
Missed deadlines: Discussion about goals/tasks that were not completed; why they weren't completed; how to avoid similar problems in the future
Time estimates: Discussion of how long task/goals took to achieve vs. how long was estimated; are estimates getting better over the course of the project?
Project progress: Is the project proceeding well? Are there systemic issues to address? Can team address them?
Team progress: Is the team working effectively and, if not, what should be done?
| Goal update | All project goals are identified in the goal stack; new goals are discussed in report.
All current phase deliverables are indentified in the goal stack; new deliverables are discussed in report.
Current risks and all major longterm risks are identified; back-up plans discussed for new risks.
Goal stack is prioritized in a way that reflects risks.
High priority goals are well described by concrete tasks and good time estimates (less than 3 hours each).
| Plan | Plan for next week is clearly described.
Plan for next week is appropriate given long term schedule.
Plan for next week is feasible.
Team member assignments and intermediate deadlines are reasonable.
Tickets were issued for work assignments.
Systemic problems with project or team identified in assessment are addressed by plan.
Trac | Deliverables | Deliverables for week are linked.
Contributions by team members recorded.
| Work log | All team members have completed log for week
Customer contact | Conference call/email | Team made contact with customer; documented by report or copy of email.
| Blog entry (after treatment completed) | Team's blog for students is interesting and understandable to audience